## Sheet1
WBS DICTIONARY
PROJECT No: 1 |  | FULL PROJECT NAME: Document Delivery Pilot Project |  |  |  | PROJECT MANAGER: Peter
ID | WBS ID | DETAILED DESCRIPTION | RESPONSIBLE PARTY/PERSON | DEPENDANCIES (WBS ID) | RESOURCE REQUIREMENTS (Human and Physical) | ESTIMATED DURATION (optional) | ESTIMATED COST (optional)
1 | 1. | Gathering Requirements
| 1.1 | Identify basic requirements | Marianne |  | Human: 1.) Application Developers 2.) Drivers 3.) Packers 4.) Application handlers 5.) Database and information team - Physical: 1.) Devices 2.) Tracking system 3.) Storage spaces 4.) Drones | 4-12 mths | $ 7,20,000
| 1.2 | Conduct user research | Marianne |  | - Human: 1.) Some trial Users 2.) Support Team - Physical: 1.) Devices 2.) Tracking system | 2-6 wks | $ 15,000
2 | 2. | System Development
| 2.1 | Develop user database | Cherry, Johnny, Williiam and Marianne |  | - Human: 1.) Database Administrator 2.) Programmer - Physical: 1.) Development Environment 2.) Database Management System 3.) Storage and Backup System 4.) Security System 5.) Testing | 2-6 wks | $ 10,000 - $ 15,000
| 2.2 | Develop Online order entry system | Marianne, Johnny, William, Cherry and Linda |  | Human: 1.) Development Team 2.) Business System Analyst 3.) Testing Specialists 4.) Programmers -Physical: 1.) Server Infrastructure 2.) Database Server 3.) Networking Equipment 4.) Software Development Tools | 10 - 12 wks | $ 4,50,000
| 2.3 | Create email, online notifications, or mobile alerts for customers | Johnny |  | Human: 1.) Programmer 2.) Business System Analyst -Physical: 1.) Integration Tools/APIs 2.) Development and Testing Tools | 2 - 3 wks | $ 10,000
| 2.4 | Develop security options | Johnny, William, Marianne, Gerald |  | Human: 1.) Security Experts 2.) Software Developers/Programmers 3.) System Architects -Physical: 1.) Hardware 2.) Networking Equipment 3.) Servers and Data Centers 4.) Security Equipment | 4-12 wks
3 | 3. | Report & Management
| 3.1 | Create performance indicators | Marianne |  | Human: 1.) Business System Analyst 2.) Collaboration with Stakeholders -Physical: 1.) Computer and Software 2.) Meeting Spaces
| 3.2 | Create sales information | Linda, Cherry, Marianne |  | Human: 1.) Business System Analyst 2.) System Programmer/Analyst 3.) Database Administrator -Physical: 1.) Software Tools 2.) Data Sources
| 3.3 | Create reports for customer reaction. | Linda, Cherry, Marianne |  | Human: 1.) Business System Analyst 2.) System Programmer/Analyst -Physical: 1.) Data storage and management: 2.) Communication tools | 4-7 wks
4 | 4. | Collaboration
| 4.1 | Establish an interface with DE | Marianne, Johnny, William, Cherry |  | Human: 1.) Business System Analyst 2.) System Programmer/Analyst 3.) Database Administrator 4.) Testing Specialists -Physical: 1.) Connectivity and Networking 2.) Communication tools 3.) Integration APIs or Protocols | 3-6 wks
| 4.2 | Deploy updated application | Johnny, William, Elizabeth, Gerald |  | Human: 1.) Application Developers 2.) System Administrators 3.) Quality Assurance/Testers -Physical: 1.) Networking Infrastructure 2.) Version Control System 3.) Networking Infrastructure | 4-11 wks | $ 3,00,000
5 | 5. | Delivery
| 5.1 | Create unique delivery code | Johnny, William, Marianne |  | Human: 1.) Programmers 2.) Business System Analyst -Physical: 1.) Collaboration Tools
| 5.2 | Perform delivery | All |  | Human: 1.) Delivery Personnel 2.) Dispatchers 3.) Customer Service Representatives 4.) Management -Physical: 1.) Drones 2.) Packaging Materials 3.) Tracking Systems 4.) Communication Devices 5.) Safety Equipment 6.) Storage and Handling Facilities
| 5.3 | Update the location of the package for customers | Johnny, William, Marianne, Cherry |  | Human: 1.) Application Developers/Programmers 2.) User Interface (UI) Designers 3.) Business Analysts or Product Managers -Physical: 1.) Computer Systems 2.) Server Infrastructure 3.) Communication Interfaces 4.) Database or Data Storage 5.) Networking and Connectivity
| 5.4 | Provide customer services | Cherry, Marianne |  | Human: 1.) Customer Service Representatives 2.) Training and Knowledge 3.) Multilingual Support 4.) Communication Tools 5.) Communication Skills 6.) Product/Service Knowledge -Physical: 1.) Workstations 2.) Telephone and Communication Tools 3.) Information Resources 4.) Computer and Technology Skills